## Sheet1
Project Title:CLASS WEBSITE DEVELOPMENT / Date of Authorization: JAN 7 / Project Start Date: JAN 7 Projected Finish Date: November 17

Key Schedule Milestones: / Complete first version of the software by June 1 / Complete production version of the software by November 17

Budget Information: The firm has allocated 1 CR. for this project, and more funds / are available if needed. The majority of costs for this project will be internal labor. All / hardware will be outsourced.Key Schedule Milestones: / Complete first version of the software by June 1 / Complete production version of the software by November 17

Project Obj: 1) design and develop user friendly website
2)enhance student communication

Project Manager : Monika Jadav

Scope: 1) home page with announcement and objective
2) syllabus page with course details and objectives
3)students login portal for accessing resources and submitting assignments
4)teachers login portal for uploading materials and grading

Stakeholder : . Students
.Administrators
.Teachers

Project deliverable :
.Fully functional classwebsites
.Training for teachers and students

Project management plan:Work breakdown system(WBS)

1)PLANNING(1 WEEK)
2)DESIGN(2 WEEKS)
3)DEVELOPMENT(4 WEEKS)
4)TESTING(1 WEEK)

RESOURCE ALLOCATION:
1)PROJECT MANAGER(MONIKA JADAV)
2)DEVELOPER(SAHIL KEDARI)
3)SPONSOR(SHREE KSHATRIYA)
4)TESTER(SHRADHA KASABE)
5)MARKETING(SHUBHAM HINGE)