## Sheet1
Project Title:E-Commerce website / Date of Authorization: JAN 7 / Project Start Date: JAN 7 Projected Finish Date:dec 17

Key Schedule Milestones: / Complete first version of the software by June 1 / Complete production version of the software by dec 17

Budget Information: The firm has allocated 10 CR. for this project, and more funds / are available if needed. The majority of costs for this project will be internal labor. All / hardware will be outsourced.Key Schedule Milestones: / Complete first version of the software by June 1 / Complete production version of the software by dec 17

Project Obj: 1) design and develop user friendly website
2)enhance shopping exp and increase the sales

Project Manager : Monika Jadav

Scope: 1) home page with promotions and feature products
2) products catalog with filter and cart options
3)order management system for order and tracking orders
4)user account for registerations,login and order history
5)shopping cart for payment gateway integration

Stakeholder : . customers
.developers
.marketing teams

Project deliverable :
.Fully functional e-commerce website
.Training for administrators

Project management plan:Work breakdown system(WBS)

1)PLANNING(1 WEEK)
2)DESIGN(2 WEEKS)
3)DEVELOPMENT(4 WEEKS)
4)TESTING(1 WEEK)
5)Launch(1 WEEK)

RESOURCE ALLOCATION:
1)PROJECT MANAGER(MONIKA JADAV)
2)DEVELOPER(SAHIL KEDARI)
3)SPONSOR(SHREE KSHATRIYA)
4)TESTER(SHRADHA KASABE)
5)MARKETING(SHUBHAM HINGE) / 6)QA Engineer(SHUBHAM JAGDALE)