## Sheet1
Task ID	Task Name	Start Date	End Date	Duration (Days)	Assigned Resource
1	Requirement Analysis	2026-03-01	2026-03-05	4	Project Manager
2	UI/UX Design	2026-03-06	2026-03-12	6	Designer
3	Frontend Development	2026-03-13	2026-03-25	12	Frontend Dev
4	Backend Development	2026-03-13	2026-03-28	15	Backend Dev
5	Database Setup	2026-03-16	2026-03-22	6	Database Admin
6	Payment Gateway Integration	2026-03-29	2026-04-05	7	Backend Dev
7	Testing & QA	2026-04-06	2026-04-15	9	QA Tester
8	Deployment & Go Live	2026-04-16	2026-04-18	2	DevOps Engineer

## Sheet2
Resource Name	Role	Total Available Days	Allocated Days (Auto)	Remaining Days
Project Manager	Management	30	30	10
Designer	UI/UX	30	30	10
Frontend Dev	Development	30	30	10
Backend Dev	Development	30	30	10
Database Admin	Database	30	30	10
QA Tester	Testing	30	30	10
DevOps Engineer	Deployment	30	30	10