## Sheet1
project charter Project Title:ERP website / Date of Authorization: JAN 7 / Project Start Date: JAN 7 Projected Finish Date:dec 17

The College ERP System is a centralized web-based application designed to manage
academic, administrative, and financial activities of a college. The system will
automate processes such as student registration, attendance tracking, examination
management, fee management, and reporting.
2. Project Objectives
- Develop a centralized database for students, faculty, and staff.
- Automate admission, attendance, examination, and fee processes.
- Provide real-time access to academic information.
- Improve efficiency and reduce paperwork.
3. Project Scope
In Scope:
- Student Information Management
- Faculty Management
- Course & Subject Management
- Attendance & Examination Module
- Fee Management System
- Report Generation
Out of Scope:
- Integration with external university systems (Phase 1)
- Mobile application development (Phase 1)
4. Stakeholders
- Project Sponsor: College Management
- Project Manager: ERP Development Lead
- Development Team
- Faculty Members
- Students
- Administrative Staff
5. Deliverables
- Requirement Specification Document
- System Design Document
- Working ERP Software
- Testing & Deployment Report
- User Manual
6. Timeline (Estimated)
- Requirement Analysis: 2 Weeks
- System Design: 2 Weeks
- Development: 6 Weeks
- Testing: 3 Weeks
- Deployment: 1 Week
7. Budget (10 cr)
- Development Cost
- Hardware/Hosting Cost
- Maintenance & Support Cost
(Final budget to be approved by management)
8. Risks
- Requirement changes
- Technical challenges
- Data security risks
- User resistance to new system
9. Approval
Project Sponsor Signature: ______sahil.k______________
Project Manager Signature: _____somnath _______________
Date: ______12/02/2026______________

WORK BREAKDOWN STRUCTURE (WBS)
College ERP System
1. Project Initiation
1.1 Define Project Scope
1.2 Identify Stakeholders
1.3 Prepare Project Charter
2. Requirement Analysis
2.1 Gather Functional Requirements
2.2 Gather Non-Functional Requirements
2.3 Requirement Documentation
2.4 Requirement Approval
3. System Design
3.1 Database Design
3.2 System Architecture Design
3.3 UI/UX Design
3.4 Design Review
4. Development
4.1 Student Management Module
4.2 Faculty Management Module
4.3 Course & Subject Module
4.4 Attendance Module
4.5 Examination Module
4.6 Fee Management Module
4.7 Report Generation Module
5. Testing
5.1 Unit Testing
5.2 Integration Testing
5.3 System Testing
5.4 User Acceptance Testing
6. Deployment
6.1 Server Setup
6.2 System Deployment
6.3 Data Migration
6.4 User Training
7. Maintenance & Support
7.1 Bug Fixes
7.2 System Monitoring
7.3 Performance Optimization
7.4 Backup & Security Management

	Requirement Description	Type	Source	Design Ref	Module	Test Case ID	Status
	User login authentication (Admin/Faculty/Student)	Functional	Stakeholder	SDD-01	Authentication Module	TC-01	Pending
	Add/Edit/Delete student records	Functional	Admin	SDD-02	Student Management	TC-02	Pending
	Manage faculty details	Functional	Admin	SDD-03	Faculty Management	TC-03	Pending
	Course & subject creation	Functional	Academic Dept	SDD-04	Course Module	TC-04	Pending
	Mark student attendance	Functional	Faculty	SDD-05	Attendance Module	TC-05	Pending
	Generate attendance reports	Functional	Faculty/Admin	SDD-06	Reporting Module	TC-06	Pending
	Conduct examination & enter marks	Functional	Faculty	SDD-07	Examination Module	TC-07	Pending
	Generate mark sheets	Functional	Admin	SDD-08	Examination Module	TC-08	Pending
	Fee payment & receipt generation	Functional	Accounts Dept	SDD-09	Fee Management	TC-09	Pending
	Generate financial reports	Functional	Accounts/Admin	SDD-10	Reporting Module	TC-10	Pending
	System should support 500+ concurrent users	Non-Functional	Management	SDD-11	System Architecture	TC-11	Pending
	Data encryption & secure login	Non-Functional	IT Policy	SDD-12	Security	TC-12	Pending
	System uptime 99% availability	Non-Functional	Management	SDD-13	Deployment	TC-13	Pending
	Backup and recovery mechanism	Non-Functional	IT Dept	SDD-14	Maintenance	TC-14	Pending
	Conduct examination & enter marks	Functional	Faculty	SDD-07	Examination Module	TC-07	Pending
	Generate mark sheets	Functional	Admin	SDD-08	Examination Module	TC-08	Pending
	Fee payment & receipt generation	Functional	Accounts Dept	SDD-09	Fee Management	TC-09	Pending
	Generate financial reports	Functional	Accounts/Admin	SDD-10	Reporting Module	TC-10	Pending
	System should support 500+ concurrent users	Non-Functional	Management	SDD-11	System Architecture	TC-11	Pending
	Data encryption & secure login	Non-Functional	IT Policy	SDD-12	Security	TC-12	Pending
	System uptime 99% availability	Non-Functional	Management	SDD-13	Deployment	TC-13	Pending
	Backup and recovery mechanism	Non-Functional	IT Dept	SDD-14	Maintenance	TC-14	Pending

## Sheet2
		Task ID	Task Name	Start Date	End Date	Duration (Days)	Assigned Resource
		1	Requirement Gathering	2026-02-01	2026-02-03	1 month	sahil
		2	Design UI/UX	2026-02-04	2026-02-08	1 month	pratham
		3	Frontend Development	2026-02-09	2026-02-18	1 month	somnath
		4	Backend Development	2026-02-09	2026-02-20	1 month	ganpati
		5	Testing & Deployment	2026-02-21	2026-02-25	1 month	bappa
		6	planning	2026-02-21	2026-02-25	1 month	somesh

Requirements Traceability Matrix (RTM) – Class Website

Req ID Requirement Description Type Source Design Ref Implementation Test Case IDStatus / R1 Website shall display products information Functional Instructor UI-01 html page tc-01 done / (product name, dates) / R2 Website shall provide catalog Functional Instructor UI-02 html page and pdf tc-02 done / R3 Website shall show announcements/updates Functional Instructor UI-03 html/css tc-03 done / R4 Website should list product and prices Functional Instructor UI-04 html/css tc-04 done

## Sheet3
Task / Activity	IT Admin	ERP User	HR / Dept Admin	ERP Vendor Support	CIO / Leadership
User Account Creation	R	I	C	C	A
Assign Roles / Permissions	R	I	C	C	A
Password Setup / Reset	R	R	C	C	I
Login Troubleshooting	R	R	I	C	I
Two-Factor Authentication Setup	R	R	I	C	I
Account Deactivation / Termination	R	I	R	C	A
Monitor Login Activity / Security	R	I	I	C	A
ERP Login Training / Guidance	R	R	C	C	I