## Sheet1
			pune rail metro charter

			Section	Details
			Project Title	Pune Metro Rail Project
			Project Sponsor	Government of Maharashtra
			Executing Agency	Maharashtra Metro Rail Corporation Limited (Maha-Metro)
			Project Manager	(sahil kedari)
			Start Date	(18/03/2021)
			Expected Completion	(6/05/2024)
			Budget	₹ 11,420 Crores (Approx.)
			Project Objective	Provide fast, safe and eco-friendly urban transport in Pune
			Project Scope	Construction of metro corridors, stations, signaling systems
			Key Stakeholders	PMC, Government of India, Citizens of Pune
			Major Deliverables	Metro lines, Stations, Rolling stock, Control system
			Risks	Cost overrun, land acquisition delays
			Assumptions	Government approvals on time
			Constraints	Budget, time, environmental clearances

			WBS FOR METRO

			1.0 Project Management
			1.1 Project Charter Development
			1.2 Stakeholder Identification
			1.3 Project Scope Definition
			1.4 Schedule Development
			1.5 Cost Estimation & Budgeting
			1.6 Risk Management Planning
			1.7 Quality Management Planning
			1.8 Communication Management

			2.0 Feasibility & Approvals
			2.1 Detailed Project Report (DPR)
			2.2 Environmental Impact Assessment
			2.3 Land Acquisition
			2.4 Government & Regulatory Approvals
			2.5 Utility Relocation Planning

			3.0 Design Phase
			3.1 Route Alignment Design
			3.2 Station Architectural Design
			3.3 Structural Design (Elevated & Underground)
			3.4 Depot Design
			3.5 Electrical System Design
			3.6 Signaling & Communication Design

			4.0 Procurement Phase
			4.1 Tender Documentation
			4.2 Contractor Selection
			4.3 Civil Works Procurement
			4.4 Rolling Stock Procurement
			4.5 Electrical & Signaling Equipment Procurement

			5.0 Construction Phase
			5.1 Civil Works
			5.1.1 Soil Testing & Survey
			5.1.2 Foundation & Piling
			5.1.3 Pier Construction
			5.1.4 Viaduct Construction
			5.1.5 Tunnel Boring (Underground)
			5.1.6 Station Construction
			5.2 Track Works
			5.2.1 Ballastless Track Installation
			5.2.2 Track Alignment & Welding
			5.3 Electrical & Signaling
			5.3.1 Overhead Electrification
			5.3.2 Power Substations
			5.3.3 Signaling System Installation
			5.3.4 Communication Network Setup

			6.0 Testing & Commissioning
			6.1 Integrated System Testing
			6.2 Trial Runs
			6.3 Safety Inspection & Certification
			6.4 Final Approval

			7.0 Operations & Maintenance
			7.1 Staff Recruitment
			7.2 Training & Capacity Building
			7.3 Control Center Setup
			7.4 Maintenance Planning
			7.5 Public Launch

Req. ID	Requirement Description	Source	WBS Link	Verification Method
R1	Provide high-capacity rapid transit in Pune	DPR	1.1, 1.3	DPR Approval Document
R2	Align corridor from Pimpri-Chinchwad to Swargate	DPR	3.1	Alignment Map Review
R3	Stations at key activity centres	DPR	3.2	Station Design Plan
R4	Underground section at high-density zones	DPR	3.3	Geotechnical Report
R5	Rolling stock capacity 4-car train sets	DPR	4.4	Vendor Contract
R6	Signaling & safety system	DPR	3.6 / 5.3	Testing & Certification Report
R7	Electrification system 25 kV AC OHE	DPR	3.5 / 5.3	Technical Inspection
R8	Minimal social & environmental impact	EIA	2.2	EIA Clearance Certificate
R9	Project completion within planned schedule	DPR	1.4 / 6	Monthly Progress Reports
R10	Budget adherence	DPR	1.5	Financial Audits
R11	Full safety certification before operations	Safety Rules	6.3	Safety Compliance Reports

			project plan

			Project Overview
			Project Title: Pune Metro Rail Project
			Sponsor: Government of Maharashtra
			Executing Agency: Maha-Metro
			Objective:
			To provide a fast, safe, eco-friendly, and efficient urban mass transit system for Pune city.

			Project Scope / ✅ In Scope / Construction of elevated & underground metro corridors / Station development / Depot construction / Electrification & signaling system / Rolling stock procurement / Testing & commissioning / ❌ Out of Scope / City bus integration management / Private land development / Smart city IT systems (separate projects)

			WBS / Project Management / Feasibility & Approvals / Design / Procurement / Construction / Testing & Commissioning / Operations Setup

Phase	Duration	Milestone
Planning	6 months	DPR Approval
Design	8 months	Design Freeze
Procurement	10 months	Contractor Award
Construction	4–5 years	Civil Completion
Testing	6 months	Safety Certification
Launch	—	Public Operations Start

Component	Estimated Cost (₹11,420 Crores)
Civil Works	5000
Rolling Stock	2000
Signaling & Electrical	1500
Land & Miscellaneous	2920
Total	~11,420 Crores

Role	Responsibility
Project Director	Overall supervision
Project Manager	Execution control
Design Engineers	Technical planning
Contractors	Construction
Safety Officer	Compliance & Safety
Operations Team	Metro running

## Sheet2
ram table

WBS ID	Activity	Sponsor	Project Director	Project Manager	Design Team	Civil Contractor	E&S Team	Safety Officer	Operations
1.1	Project Charter Approval	A	R	C	-	-	-	-	-
1.4	Schedule Planning	C	A	R	C	-	-	-	-
2.1	DPR Preparation	C	A	R	R	-	-	-	-
3.1	Alignment Design	-	C	A	R	-	-	-	-
4.2	Contractor Selection	A	R	R	-	-	-	-	-
5.1	Civil Construction	-	C	A	C	R	-	C	-
5.3	Electrification & Signaling	-	C	A	C	-	R	C	-
6.2	Trial Runs	-	C	A	C	R	R	R	C
7.5	Public Launch	A	R	R	-	-	-	C	R

## Sheet3
	raci chart

Activity	Sponsor	Project Director	Project Manager	Design Team	Contractor	E&S Team	Safety Officer	Operations
Project Planning	A	C	R	C	-	-	-	-
DPR Approval	A	R	C	C	-	-	-	-
Design Finalization	-	A	C	R	-	C	-	-
Civil Work Execution	-	C	A	C	R	-	C	-
Electrical Installation	-	C	A	-	-	R	C	-
Safety Inspection	-	C	A	-	-	C	R	-
Trial Testing	-	C	A	C	R	R	R	C
Operations Handover	A	R	C	-	-	-	C	R