## Sheet1
Task ID	Task Name	Start Date	End Date	Duration (Days)	Assigned Resource
1	Requirement Gathering	2026-02-01	2026-02-03	1 month	sahil
2	Design UI/UX	2026-02-04	2026-02-08	1 month	prathmesh
3	Frontend Development	2026-02-09	2026-02-18	1 month	shubham
4	Backend Development	2026-02-09	2026-02-20	1 month	pranav
5	Testing & Deployment	2026-02-21	2026-02-25	1 month	shree
6	planning	2026-02-21	2026-02-25	1 month	siddesh

## Sheet2
Resource Name	Role	Total Available Days	Allocated Days (Auto)	Remaining Days
sahil	Developer	20	1 month	5 days
prathmesh	Designer	20	1 month	10 days
pranav	Backend/Tester	20	1 month	2 days